## Sheet1
Start Date | Finish Date | Planned work | Achieved work | Notes
2021-01-21 | 2021-01-21 | I need attend first lecture and know what you need to do. |  | I need to make gantt charts to start the project inistially.
2021-01-28 | 2021-01-28 | I need to attend lecture to know what to do. | I started making gantt charts. | I need to complete the task for week 2 to be able to follow along the project.
2021-02-04 | 2021-02-04 | I need to attend lecture to know what to do. |  | I still haven't been able to do the tasks for week 2 properly I need to ask Richard to help me understand them better or learn basic matlab.
2021-02-11 | 2021-02-11 | I need to attend lecture to know what to do. |  | I tired doing the task for week 2 again, I still haven't asked Richard. I need to better manage my time between my private and study/work related life.
2021-02-11 | 2021-02-16 | Now I need to do the task for the parallel processing week. | I have asked richard what to do he has helped me and I can write functions I MATLAB. | Scripts work like python seprate pages and functions in both langues act the same but the syntax is different.
2021-02-18 | 2021-02-18 | I need to attend lecture to know what to do. |  | This lecture will be usefull later when I need to write my report but right now I still haven't been able to understand the parallel processing tasks I either need to undersatnd it better or ask Richard to explain it to me.
2021-02-25 | 2021-02-25 | I need to attend lecture to know what to do. |  | I need to focus on the maths module now for the up coming test.
2021-03-04 | 2021-03-04 | I need to attend lecture to know what to do. |  | Completed the maths test today so now I can focus more on the project.
2021-03-05 | 2021-03-16 | I need to ask Richard about the parallel processing task and I need to make my simple sample flow charts to get the work going. | I haved asked Richard for help after getting a better understanding of the task I was able to do it. I have made initial flow charts. | The coding related task seem easier then I thought they would be but using MATLAB seems to be the biggest challenge for me. I think planning is going to be assesed far hevier then coding and Richard keeps stating its importance so I need to plan better. I also need better counsil i've found some methimetical problems like Ahmdel's law and the recomendation of HPC as recommened by Richard but i can't understand them with my level of methametical skills. I need to use the sigma support centre and ask poeple equiped better methametically for help and guidence.
2021-03-17 | 2021-03-19 | I need to do the automated testing. | I have done initial automation tetsing. | I don't think I understand completely what automation is or how it would be defined by other people. I don't know if I'll have to automate the whole test or just the error tests. I need to ask Richard and some of my friends as they would know better. I wan't able to attend the lecture but my friends asked Richard about Ahmdals law so i need to ask them about that later.
2021-03-20 | 2021-03-24 | I need to make a prototype or a template project that I can work and build on later as exam are coming so I won't have much time for the project related work. | I have made a basic husk for my over all project. I can use this to build the full scale project later on. I have manged to automate the graphs and the error tests. | There was an error for the esemblevectorpar but with Richards help I've changed the it's value it funtions better. We have also chaged the values oor numlocations.
2021-03-25 | 2021-04-14 | I need to focus on the upcoming exams so I won't do much work for this module. I have basic code needed to pass the Viva. I need to deffer the 5005 exam so I can get better marks. | I still managed to do a lot of work. As the essemblevectorpar was still giving me a issue I manged to slove the problem by adding the code under the for loop so it doesn’t change size as often and I did the same for T3 as my time was coming inaccurate. I have also made a initial video for the viva so if the worst case happens i can at least pass the Viva. The content of the video is good but the audio quality is quite bad. | I got some feedback from Richard he said my video had all the content but was lacking speed.
2021-04-14 | 2021-02-16 | I need to finsh the viva video. | I have made the viva video. | I haved ordered a head set to improve my audio quality but it doesn’t work. I have called the microsoft team and installed all the software but still my audio quailty is quite bad. I have downloaded some audio software to improve the audio quality but they don't work either. I've found an app called Krisp which has improved the audio quality. Now i can soley focus on 5011 related work and finsh my project.
2021-02-16 | 2021-04-30 | I need to learn MATLAB properly. I need to improve my flow charts. I need to automate everthing. I need to write my report. | I didn't learn MATLAB but one of my friends has told me about MATLABS help function which has made doing all the tasks trival. I have improved my flow charts. I have automated everthing but I am using interp1 to give recommended processors after reserching i have concluded that polyfit works better for this i have decided to use it. Everthing works as intended. I have written my report. | There was a lot of trial and error in writing all of these tasks and it has shown me how much important project planning can be. I have leraned that moving from programing langues can be a bit easier then I initially thought and I have changed my apporoach to that. In the begening i was struggling with the basic maths work but i had no understanding of what the code was actually doing after learing about the help function i was able to do all the task without much effort. I could have made my error testing code a bit better by using the same script for -9999 and NaN error automation and generation codes. I will try to take this experince and focus more on the planing side of pograming from now on as i could have done most of this programming optimally if i had just done that from the start.